## Sheet1
Sr # | Module | Level | Hrs Min | Hrs Max | Day
1 | Overall App UI with animations as described in the document | Low | 6 | 8 | Friday
2 | Record video in pieces (with pause/resume) and combine pieces together at the end (to make a single video) | Low | 3 | 5 | Friday
3 | Custom Progress Bar showing circular Recording with Pause, Resume & chunk cut(s) | Low | 3 | 3 | Friday
4 | Video preview screen playing the video automatically after capture is complete (or after user presses > right arrow) | Medium | 2 | 4 | Friday
5 | Enter comment (up to 118 chars) in the share screen after video preview | Low | 2 | 3 | Monday
6 | Go back to video preview if user presses the video thumbnail on the share screen | Low | 2 | 4 | Monday
7 | Upload video to server along with the user comment (if any entered) | Medium | 4 | 6 | Monday
8 | After uploading to server switch to Feed screen, showing the just recorded video/comment on top | High | 4 | 6 | Monday
9 | Once the Feed screen is launched, check to see if there are new videos available on the server, and if so download them and store on the device (download the more recent ones first to show them earlier in the feed screen) | Medium | 4 | 6 | Tuesday
10 | Ping the server periodically to see if there are new videos, and if so download them and store on the device (again, download the more recent ones first - the server API provides means to do that) | Medium | 4 | 5 | Tuesday
11 | Play video that is on focus (in a loop) on Feed screen | Medium | 4 | 5 | Tuesday
12 | Scrolling Feed Screen and Loading data efficiently during Scrolling | High | 3 | 4 | Tuesday
13 | Smile Counts & Feed page data updates periodically | High | 3 | 4 | Tuesday
|  | TOTAL Hrs | 0 | 63
|  | FINAL Target Hrs | 16.75

## Questions
Will the user login in the App? What are its details?
How many videos to load at a time 10 or less?
Webservice: What you say how much time your services will take to download 10 videos and its data? And what data, pics etc other than video it will contain?
Tagging to Celbity? Fom where and how celeberity and contacts will come?
On feed screen how tags are coimg?
What alog is to get top 10 videos and next 10 videos?